## Project Charter
LEAN SIX SIGMA BLACK BELT PROJECT CHARTER
Project Title | Improving Customer Order Fulfillment Reliability Using Lean Six Sigma DMAIC
Business Case | Customer order fulfillment is a critical supply-chain service outcome. The existing analytics project provides a baseline view of fulfillment performance; this project investigates sources of variation and improvement opportunities using DMAIC.
Problem Statement | Customer demand is not consistently fulfilled in full. The available order data contains multiple fulfillment outcomes, but the specific drivers of variation have not yet been statistically validated.
Project Goal | Establish a validated baseline, identify significant sources of fulfillment variation, develop evidence-based improvement actions, and establish a control strategy. A numerical improvement target will be finalized during Measure after the baseline is formally defined.
Primary CTQ | Customer Order Fulfillment
Primary Y | Customer Quantity Fill Rate (%) = Total Quantity Shipped / Total Quantity Ordered × 100. Final inclusion/exclusion and aggregation rules will be locked during Measure.
Secondary Measures | Complete-order rate; partial fulfillment rate; backorder rate; cancellation rate; shortage quantity; on-time fulfillment/delivery; supplier fill rate; supplier delivery performance; inventory availability; reorder-point status.
Candidate Xs | Inventory availability, closing inventory, reorder point, safety stock, stock position vs. reorder point, product/category/demand/lead time/shelf life, supplier performance, warehouse, order quantity/date/status, shipment quantity, and relevant replenishment measures.
Scope - In | Customer sales-order fulfillment; ordered vs. shipped quantities; product and warehouse fulfillment; inventory availability; reorder-point status; supplier performance; purchase-order fulfillment; relevant inventory movements; statistical analysis; improvement and control recommendations.
Scope - Out | Pricing, marketing, financial accounting, transportation-network optimization beyond available data, workforce optimization unless additional data is added, and changes to actual company operations.
Process Boundary | Customer Order Created → Order Processing → Inventory Availability Check → Allocation → Replenishment if Required → Picking/Fulfillment → Shipment → Customer Order Fulfilled/Unfulfilled
Data Source | Synthetic FMCG-style dataset containing Products, Suppliers, Warehouses, Customers, Inventory, Sales Orders, and Purchase Orders.
Portfolio Positioning | Existing project answers: 'What is happening in the supply chain?' This LSSBB project answers: 'Why is the fulfillment problem happening, and how can the process be systematically improved?'
Project Principle | Do not declare a root cause or improvement action before the relevant data has been analyzed. Distinguish observed facts, hypotheses, statistical evidence, operational interpretation, and recommendations.

## SIPOC
CUSTOMER ORDER FULFILLMENT — SIPOC
Suppliers | Inputs | Process | Outputs | Customers
Product Suppliers | Products | 1. Customer places order | Order confirmation | Customers
Procurement | Inventory availability | 2. Order is processed | Allocated quantity | Customers
Suppliers | Purchase Orders | 3. Inventory availability is assessed | Fulfilled quantity | Sales / Customer Service
Warehouses | Warehouse inventory | 4. Inventory is allocated | Shortage / backorder | Supply Chain
Internal Planning | Replenishment information | 5. Order is picked/fulfilled | Shipment | Management
Customers | Customer demand | 6. Order is shipped | Delivery information | Finance / Operations
Process boundary |  | Start: Customer order is created |  | End: Customer order is fulfilled/shipped or identified as unfulfilled

## VOC_CTQ
VOC → CTQ TREE
Customer Need | Customer Requirement | CTQ | Measure / KPI | Status
Reliable Order Fulfillment | Receive the required quantity | Quantity Fulfillment | Customer Quantity Fill Rate (%) | Primary CTQ
Reliable Order Fulfillment | Receive the order within the expected timeframe | Fulfillment Timeliness | On-Time Fulfillment / Delivery Rate | Secondary CTQ
Reliable Order Fulfillment | Receive the order completely | Fulfillment Completeness | Complete Order Fulfillment Rate | Secondary CTQ
Reliable Order Fulfillment | Avoid unmet demand | Shortage / Backorder | Shortage Quantity; Backorder Rate | Secondary CTQ
Reliable Order Fulfillment | Maintain upstream supply reliability | Supplier Reliability | Supplier Fill Rate; Supplier Delivery Performance | Supporting metric
Reliable Order Fulfillment | Maintain product availability | Inventory Availability | Availability / Reorder-Point Status | Candidate driver / supporting metric
VOC data limitation